## Logistics
Logistics Daily Discipline Report
Andaman and East Coast Offshore Drilling Campaign (AEC-OFFSHORE) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
OSD-2297 | OSD-2297-01 | W2 - bulk cement, barite and mud chemical supply | TONNE | 2189 | 442 | 7 | 449 | 20.5 | Ongoing
OSD-2296 | OSD-2296-01 | W2 - supply vessel runs and material transfers | NOS | 44 | 0 | 1 | 1 | 2.4 | Ongoing

## Drilling
Drilling Daily Discipline Report
Andaman and East Coast Offshore Drilling Campaign (AEC-OFFSHORE) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
OSD-2310 | OSD-2310-01 | W3 - drive conductor and spud | M | 110 | 0 | 1 | 1 | 1 | Ongoing
OSD-2320 | OSD-2320-01 | W3 - drill 26 in hole section | M | 446 | 0 | 1 | 1 | 0.3 | Ongoing
OSD-2330 | OSD-2330-01 | W3 - run and cement 20 in casing | TONNE | 160 | 0 | 1 | 1 | 0.7 | Ongoing
OSD-2340 | OSD-2340-01 | W3 - drill 17.5 in hole section | M | 1042 | 0 | 3 | 3 | 0.4 | Ongoing
OSD-2350 | OSD-2350-01 | W3 - run and cement 13.375 in casing | TONNE | 210 | 0 | 1 | 1 | 0.6 | Ongoing
OSD-2360 | OSD-2360-01 | W3 - drill 12.25 in hole section | M | 1265 | 0 | 4 | 4 | 0.4 | Ongoing