## Civil
Civil Daily Discipline Report
Siliguri-Mughalsarai Petroleum Products Pipeline (SMP-PIPE) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
SMP-1010 | SMP-1010-01 | Land acquisition and ROW compensation | NOS | 14952 | 0 | 45 | 45 | 0.4 | Ongoing
SMP-1020 | SMP-1020-01 | Route survey and alignment sheets | KM | 534 | 0 | 2 | 2 | 0.5 | Ongoing

## Logistics
Logistics Daily Discipline Report
Siliguri-Mughalsarai Petroleum Products Pipeline (SMP-PIPE) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
SMP-2000 | SMP-2000-01 | Line pipe procurement and delivery | TONNE | 20292 | 0 | 61 | 61 | 0.4 | Ongoing
SMP-2010 | SMP-2010-01 | Valves, fittings and pig traps delivery | NOS | 101 | 0 | 1 | 1 | 1.1 | Ongoing

## Piping
Piping Daily Discipline Report
Siliguri-Mughalsarai Petroleum Products Pipeline (SMP-PIPE) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
SMP-3110 | SMP-3110-01 | Pipe stringing - Spread 1 Siliguri-Purnea | KM | 140 | 0 | 1 | 1 | 0.8 | Ongoing
SMP-3120 | SMP-3120-01 | Pipe welding - Spread 1 Siliguri-Purnea | JOINT | 11475 | 0 | 34 | 34 | 0.4 | Ongoing
SMP-3130 | SMP-3130-01 | NDT and radiography - Spread 1 Siliguri-Purnea | JOINT | 11475 | 0 | 34 | 34 | 0.4 | Ongoing
SMP-3140 | SMP-3140-01 | Field joint coating - Spread 1 Siliguri-Purnea | JOINT | 11475 | 0 | 34 | 34 | 0.4 | Ongoing