## Piping
Piping Daily Discipline Report
Numaligarh Refinery Expansion (NRL-EXPANSION) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
NRE-4050 | NRE-4050-01 | Hydrotreater piping joints welded | JOINT | 18998 | 4950 | 115 | 5065 | 25.8 | Ongoing
NRE-2080 | NRE-2080-01 | CDU2 hot insulation cladding | M2 | 87400 | 38755 | 580 | 39335 | 45.2 | Ongoing

## Electrical
Electrical Daily Discipline Report
Numaligarh Refinery Expansion (NRL-EXPANSION) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
NRE-2060 | NRE-2060-01 | CDU2 LV panel installed | NOS | 106 | 27 | 1 | 28 | 25.3 | Ongoing
NRE-4060 | NRE-4060-01 | Hydrotreater MCC panel installed | NOS | 74 | 40 | 1 | 41 | 54.5 | Ongoing

## Instrumentation
Instrumentation Daily Discipline Report
Numaligarh Refinery Expansion (NRL-EXPANSION) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
NRE-2070 | NRE-2070-01 | CDU2 loops terminated and checked | NOS | 3335 | 835 | 14 | 849 | 25.5 | Ongoing
NRE-7020 | NRE-7020-01 | DCS cabinet installed | NOS | 24 | 7 | 1 | 8 | 32.2 | Ongoing

## Structural
Structural Daily Discipline Report
Numaligarh Refinery Expansion (NRL-EXPANSION) ¦ Report date: 30 Sep 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
NRE-2020 | NRE-2020-01 | CDU2 structural steel erected | TONNE | 3200 | 2496 | 36 | 2532 | 79.1 | Ongoing