SITE PROGRESS NOTE - 2026-09-30

Report date: 2026-09-30

Numaligarh Refinery Expansion (NRL-EXPANSION)

Reporting period: 0800 h to 1800 h

WORK EXECUTED

1. NRE-2020 | Structural | CDU2 structural steel erection continued on the pipe rack.

Today: 35 tonnes | Cumulative: 2531/3200 tonnes | Physical progress: 79.1%

2. NRE-4050 | Piping | Hydrotreater process piping joints welded.

Today: 110 joints | Cumulative: 5060/18998 joints | Physical progress: 25.8%

3. NRE-4060 | Electrical | Hydrotreater MCC panel installed in substation SS-4.

Today: 1 nos | Cumulative: 41/74 nos | Physical progress: 54.5%

4. NRE-7020 | Instrumentation | DCS cabinet set and anchored in the control room.

Today: 1 nos | Cumulative: 8/24 nos | Physical progress: 32.2%

Prepared by: R. Baruah, Site Engineer

Fictional demonstration data for ANVYRA. Not a real project record.