SITE PROGRESS NOTE - 2026-09-30

Report date: 2026-09-30

Siliguri-Mughalsarai Petroleum Products Pipeline (SMP-PIPE)

Reporting period: 0800 h to 1800 h

WORK EXECUTED

1. SMP-1010 | Civil | Land acquisition and ROW compensation.

Today: 60 nos | Cumulative: 60/14952 nos | Physical progress: 0.5%

2. SMP-1020 | Civil | Route survey and alignment sheets.

Today: 2 km | Cumulative: 2/534 km | Physical progress: 0.5%

3. SMP-2000 | Logistics | Line pipe procurement and delivery.

Today: 81 tonnes | Cumulative: 81/20292 tonnes | Physical progress: 0.5%

4. SMP-2010 | Logistics | Valves, fittings and pig traps delivery.

Today: 1 nos | Cumulative: 1/101 nos | Physical progress: 1.1%

Prepared by: R. Baruah, Site Engineer

Fictional demonstration data for ANVYRA. Not a real project record.